## tugas 6
Activity | Predecessor | Duration | 2016 | [6 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
|  |  | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March
1a | - | bar: 2016 June to 2016 Sept
1b | 1a | bar: 2016 Sept to 2017 Feb
1c | 1a | bar: 2016 Sept to 2016 Nov
2a | 1b, 1c | bar: 2017 Feb to 2019 Feb
2b | 1b, 1c | bar: 2017 Feb to 2018 Feb
2c | 2b | bar: 2017 Feb to 2018 Feb
2d | 2c | bar: 2018 Feb to 2018 March
2e | 2b | bar: 2018 Feb to 2019 Feb
3a | 2a, 2d, 2e | bar: 2019 Feb to 2019 March
3b | 2a, 2d, 2e | bar: 2019 Feb to 2019 March

## tugas 7 (2b)
Aktivitas | Predecessor | Waktu (Bulan) | Biaya per bulan ($ 1000) | Slack time | Jadwal
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
A | - | 1 | 210 | 0 | Jadwal 1: 210
B | A | 4 | 30 | 2 | Jadwal 2: 30; Jadwal 3: 30; Jadwal 4: 30; Jadwal 5: 30
C | A | 3 | 120 | 0 | Jadwal 2: 120; Jadwal 3: 120; Jadwal 4: 120
D | A | 2 | 150 | 3 | Jadwal 2: 150; Jadwal 3: 150
E | B | 2 | 150 | 2 | Jadwal 6: 150; Jadwal 7: 150
F | C | 2 | 60 | 0 | Jadwal 5: 60; Jadwal 6: 60
G | F, D | 3 | 60 | 0 | Jadwal 7: 60; Jadwal 8: 60; Jadwal 9: 60
Anggaran ($ 1000) |  |  |  |  | 210 | 300 | 300 | 150 | 90 | 210 | 210 | 60 | 60

## Tugas 7 (2c)
Aktivitas | Predecessor | Waktu (Bulan) | Biaya per bulan ($ 1000) | Slack time | Jadwal
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
A | - | 1 | 210 | 0 | Jadwal 1: 210
B | A | 4 | 30 | 2 | Jadwal 2: 30; Jadwal 3: 30; Jadwal 4: 30; Jadwal 7: 30
C | A | 3 | 120 | 0 | Jadwal 2: 120; Jadwal 3: 120; Jadwal 4: 120
D | A | 2 | 150 | 3 | Jadwal 5: 150; Jadwal 6: 150
E | B | 2 | 150 | 2 | Jadwal 8: 150; Jadwal 9: 150
F | C | 2 | 60 | 0 | Jadwal 5: 60; Jadwal 6: 60
G | F, D | 3 | 60 | 0 | Jadwal 7: 60; Jadwal 8: 60; Jadwal 9: 60
Anggaran ($ 1000) |  |  |  |  | 210 | 150 | 150 | 150 | 210 | 210 | 90 | 210 | 210